Technology, Engineering, and Computing

(TEC) BUSINESS CENTER

5200 Engineering Hall, Zot 2700

HSSoE & Calit2

Recommended Schedule for Preparing & Submitting a Proposal:

| Common Elements of a Proposal | Process (Responsibility) – PI, Research Development | Process (Responsibility) TEC Financial Analyst | Recommended Schedule (to meet SPA Deadline of 5 business days prior to agency deadline for standard proposal and 7 business days prior to agency deadline for non-standard proposal) |
| --- | --- | --- | --- |
| Call for Proposal | - Read sponsor guidelines to identify proposal requirements and restrictions. - Use the TEC proposal in-take system to submit request. | - Read sponsor guidelines to identify proposal requirements and restrictions. - Prepare a draft budget based on PI in-take entry. - Reach out to PI if there are any questions. | As soon as it is determined a proposal will be submitted or no later than two (2) business weeks prior to SPA deadlines. |
| Subcontract Subrecipient Commitment Form, Subrecipient v. Contractor Determination Form, Commitment Letter (if applicable), statement of work, budget & justification, and any other required proposal elements. | - Coordinate with subcontract PI on proposal, statement of work, budget, budget justification, and signed commitment letter from other institution. - Provide contact information for the staff in subcontract institutions. | - Provide assistance with obtaining signatures on subrecipient commitment form - Coordinate with Subaward institutions for proposal package. - Upload final package in Kuali Research (KR). | One (1) business week prior to SPA deadline for non-standard proposals. |

| Common Elements of a Proposal | Process (Responsibility) – PI, Research Development | Process (Responsibility) TEC Financial Analyst | Recommended Schedule (to meet SPA Deadline of 5 business days prior to agency deadline for standard proposal and 7 business days prior to agency deadline for non-standard proposal) |
| --- | --- | --- | --- |
| Budget Detail & Budget Justification | - Identify budget targets and specific project needs. - Finalize budget detail. Allow time for 2-3 drafts. - Review and provide input to finalize budget justification. | - Provide budget worksheet to PI as resource for presenting budget. - Develop draft budget detail and collaborate with PI to finalize. - Develop draft budget justification. | Budget drafts to be started as soon as it is determined a proposal will be submitted. No later than one (1) business week prior to SPA deadline. The budget should be final at least three (3) business days prior to SPA deadline. *Budget changes will not be accepted after the proposal is routed through KR. |
| Other Attachments (if applicable): Cost Share, Consultant Commitment Letter(s); Letters of Support, Collaboration and/or Commitment. | -Initiate requests. Coordinate as needed on campus to secure the necessary letters or documents. | -Upload necessary documents in KR. | At least two (2) business weeks prior to SPA non-standard deadline. |

| Common Elements of a Proposal | Process (Responsibility) – PI, Research Development | Process (Responsibility) TEC Financial Analyst | Recommended Schedule (to meet SPA Deadline of 5 business days prior to agency deadline for standard proposal and 7 business days prior to agency deadline for non-standard proposal) |
| --- | --- | --- | --- |
| Other Support - Current Awards & Pending Proposals (project sponsor, title, period, total cost, & % effort by PI) . | - Update all information once TEC analyst submits draft document - Obtain information from other campus units as needed. | - Prepare a draft of current and pending utilizing submission history as soon as budget is finalized. | At least three (3) business days before SPA deadline. |
| Biographical Sketch for key personnel. | - Update biosketch as necessary. -Upload documents in appropriate proposal application file (ie Fastlane, grants.gov or other) or delegate to TEC analyst. | -Upload documents in appropriate proposal application file (ie Fastlane, grants.gov or other) if delegated task. | One (1) week prior to SPA deadline. |
| Facilities document for applicable sponsor. | - Update facilities document as necessary. -Upload documents in appropriate proposal application file (ie Fastlane, grants.gov or other) or delegate to TEC analyst. | -Upload documents in appropriate proposal application file (ie Fastlane, grants.gov or other) if delegated task. | One (1) week prior to SPA deadline. |
| Financial Disclosure / Conflict of Interest Form(s) (if applicable) | - Submit completed and signed form once analyst determines the appropriate forms to use for the proposal or complete annual COI online. | - Provide applicable conflict of interest financial disclosure form to PI for signature | As soon as the budget is finalized. At least three (3) business days prior to SPA deadline. |

| Common Elements of a Proposal | Process (Responsibility) – PI, Research Development | Process (Responsibility) TEC Financial Analyst | Recommended Schedule (to meet SPA Deadline of 5 business days prior to agency deadline for standard proposal and 7 business days prior to agency deadline for non-standard proposal) |
| --- | --- | --- | --- |
| Regulatory Committee Approvals: Human Subjects - Institutional Review Board (IRB); or Animal Care & Use - Institutional Animal Care and Use Committee (IACUC); Export Controls; Institutional Biosafety (IBC); Human Stem Cell Research Oversight (hSCRO) | - Regulatory committee approvals/pending approvals are required at the time of proposal. - Provide answers to TEC analyst for KR compliance questions | - Answer KR compliance questions as provided by the PI. | Required document for submission to SPA by published lead times. The proposal can be submitted if committee approvals are pending. |
| Scope of work, Project Summary and Description (Technical Sections of the proposal) | Send or upload draft documents of the scope of work, project summary and/or description as required by the sponsor. PI responsible for all required components of a proposal per the solicitation. | -Upload documents in appropriate proposal application file (ie Fastlane, grants.gov or other) if delegated task. | One (1) week prior to SPA deadline. |
| Kuali Research (KR) | - Certify Kuali Research submission (PI) by approving online. | - Initiate and prepare proposal application in Kuali Research route though work flow - Monitor KR work flow. | Three (3) business days prior to SPA routing deadline. As soon as notification received. Follow up with signing officials. |

| Common Elements of a Proposal | Process (Responsibility) – PI, Research Development | Process (Responsibility) TEC Financial Analyst | Recommended Schedule (to meet SPA Deadline of 5 business days prior to agency deadline for standard proposal and 7 business days prior to agency deadline for non-standard proposal) |
| --- | --- | --- | --- |
| Final Submission Electronic Paper | - Notify analyst or Sponsored Project Officer that electronic file is final and ready to be submitted. | - Coordinate with SPA for final review and submission. - Coordinates the mailing of paper submissions or Univ. letters of endorsement. *PI responsibility for any postage required for submission. | The final scope of work/technical section should be submitted to SPA no later than eight (8) business hours before the Sponsor deadline. Three (3) business days prior to agency deadline or as guidelines direct. |